## Sheet1
System / Title Name: | Paws for Home ( Pet Adoption System )
Members: | Catubig, Niña Margarette
Evangelista, Kaye Aizerner
Vasquez, Kyle T.
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | September |  |  |  | October |  |  |  | November |  |  |  | December
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
INDEX (LANDING PAGE) | Vasquez, Kyle T. | 2024-10-01 | 2024-10-02 | Done | bar: September 4 to October 1
NAVBAR BUTTONS | Catubig, Niña Margarette | 2024-10-01 | 2024-10-02 | Done | bar: September 4 to October 1
SIGN-UP | Vasquez, Kyle T. | 2024-09-30 | 2024-10-02 | Done | bar: September 4 to October 1
LOGIN | Catubig, Niña Margarette | 2024-10-01 | 2024-10-02 | Done | bar: September 4 to October 1
LOGOUT | Evangelista, Kaye Aizerner | 2024-10-02 | 2024-10-02 | Done | bar: September 4 to October 1
BROWSE PET | Evangelista, Kaye Aizerner | 2024-10-13 | 2024-10-14 | Done | bar: October 2 to October 3
VIEW PET | Evangelista, Kaye Aizerner | 2024-10-14 | 2024-10-15 | Done | bar: October 2 to October 3
ADOPTION APPLICATION | Vasquez, Kyle T. | 2024-10-12 | 2024-10-13 | Done | bar: October 2 to October 3
MESSAGE | Evangelista, Kaye Aizerner | 2024-10-13 | 2024-10-14 | Done | bar: October 2 to October 4
FEATURES AND CONTACT US | Vasquez, Kyle T. | 2024-10-12 | 2024-10-13 | Done | bar: October 2 to October 3
SHELTER DASHBOARD | Vasquez, Kyle T. | 2024-10-13 | 2024-10-14 | Done | bar: October 2 to October 4
PET LISTING | Evangelista, Kaye Aizerner | 2024-10-15 | 2024-10-16 | Done | bar: October 2 to October 3
ADD PET | Evangelista, Kaye Aizerner | 2024-10-01 | 2024-10-02 | Done | bar: September 4 to October 1
PENDING REQUEST | Evangelista, Kaye Aizerner | 2024-10-18 | 2024-10-26 | Done | bar: October 4 to November 1
PENDING REQUEST (POP UP) | Evangelista, Kaye Aizerner | 2024-10-18 | 2024-10-26 | Done | bar: October 4 to November 1
PET ADOPTED | Evangelista, Kaye Aizerner | 2024-10-18 | 2024-10-26 | Done | bar: October 4 to November 1
USER DASHBOARD | Catubig, Niña Margarette | 2024-10-09 | 2024-10-14 | Done | bar: October 2 to October 3
USER REQUESTS | Catubig, Niña Margarette | 2024-10-13 | 2024-10-15 | Done | bar: October 2 to October 3
USER FAVORITES | Evangelista, Kaye Aizerner | 2024-10-18 | 2024-10-26 | Done | bar: October 4 to November 1
USER HISTORY | Catubig, Niña Margarette | 2024-10-18 | 2024-10-26 | Done | bar: October 4 to November 1
PROFILE FILLING | Catubig, Niña Margarette | 2024-10-09 | 2024-10-12 | Done | bar: October 2 to October 3
PROFILE EDITING | Catubig, Niña Margarette | 2024-10-18 | 2024-10-26 | Done | bar: October 4 to November 1
ADOPTION APP VIEW (SHELTER) | Vasquez, Kyle T. | 2024-10-18 | 2024-10-26 | Done | bar: October 4 to November 1
UI INDEX | Vasquez, Kyle T. | 2024-10-18 | 2024-10-26 | To-Do | bar: October 4 to November 1
UI NAV BAR | Vasquez, Kyle T. | 2024-10-18 | 2024-10-26 | To-Do | bar: October 4 to November 1
UI SIGNUP | Vasquez, Kyle T. | 2024-11-02 | 2024-11-09 | To-Do | bar: November 2 to November 3
UI LOGIN | Evangelista, Kaye Aizerner | 2024-11-02 | 2024-11-09 | To-Do | bar: November 2 to November 3
UI BROWSE | Evangelista, Kaye Aizerner | 2024-11-02 | 2024-11-09 | To-Do | bar: November 2 to November 4
UI VIEW PET (POP UP) | Evangelista, Kaye Aizerner | 2024-11-02 | 2024-11-09 | To-Do | bar: November 2 to November 3
UI ADOPTION APP | Catubig, Niña Margarette | 2024-11-03 | 2024-11-10 | To-Do | bar: November 2 to November 3
UI MESSAGE | Catubig, Niña Margarette | 2024-11-04 | 2024-11-11 | To-Do | bar: November 2 to November 3
UI DASHBOARD (SHELTER) | Catubig, Niña Margarette | 2024-11-05 | 2024-11-12 | To-Do | bar: November 2 to November 3
UI PET LISTINGS | Vasquez, Kyle T. | 2024-11-06 | 2024-11-13 | To-Do | bar: November 2 to November 3
UI ADD PET | Vasquez, Kyle T. | 2024-11-07 | 2024-11-14 | To-Do | bar: November 2 to November 3
UI PENDING REQUEST | Vasquez, Kyle T. | 2024-11-15 | 2024-11-23 | To-Do | bar: November 4 to December 1
UI PENDING REQUEST(POP UP) | Evangelista, Kaye Aizerner | 2024-11-15 | 2024-11-23 | To-Do | bar: November 4 to December 1
UI PETS ADOPTED | Evangelista, Kaye Aizerner | 2024-11-15 | 2024-11-23 | To-Do | bar: November 4 to December 1
UI DASHBOARD (USER) | Evangelista, Kaye Aizerner | 2024-11-15 | 2024-11-23 | To-Do | bar: November 4 to December 1
UI REQUEST USER | Catubig, Niña Margarette | 2024-11-15 | 2024-11-23 | To-Do | bar: November 4 to December 1
UI FAVORITES | Catubig, Niña Margarette | 2024-11-15 | 2024-11-23 | To-Do | bar: November 4 to December 1
UI ADOPTION HISTORY | Catubig, Niña Margarette | 2024-11-15 | 2024-11-23 | To-Do | bar: November 4 to December 1
UI PROFILE | Catubig, Niña Margarette | 2024-11-15 | 2024-11-23 | To-Do | bar: November 4 to December 1
UI EDIT PROFILE | Catubig, Niña Margarette | 2024-11-15 | 2024-11-23 | To-Do | bar: November 4 to December 1
UI ADOPTION APP VIEW | Vasquez, Kyle T. | 2024-11-15 | 2024-11-23 | To-Do | bar: November 4 to December 1
EDIT/ARCHIVE PET | Vasquez, Kyle T. | 2024-11-15 | 2024-11-23 | To-Do | bar: November 4 to December 1

## Detailed and Readable Gantt Cha
| System / Title Name: | Paws for Home ( Pet Adoption System )
| Members: | Catubig, Niña Margarette
Evangelista, Kaye Aizerner
Vasquez, Kyle T.
| Statuses |  | Todo
In-Progress
Done
On-hold
[6 empty] | September |  |  |  | October |  |  |  | November |  |  |  | December
Tasks |  | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
LOGIN
| Login Functionalities | Vasquez, Kyle T. | 2024-10-01 | 2024-10-02 | Done | bar: September 4 to December 1
| Login UI with Styles | Vasquez, Kyle T. | 2024-10-03 | 2024-10-03 | Done | bar: October 1 to December 1
| Login Enhanced UI | Evangelista, Kaye Aizerner | 2024-11-02 | 2024-11-09 | Done | bar: October 1 to December 1
SIGN UP
| Sign Up Functionalities | Catubig, Niña Margarette | 2024-09-30 | 2024-10-02 | Done | bar: September 4 to December 1
| Sign Up UI with Styles | Catubig, Niña Margarette | 2024-10-14 | 2024-10-14 | Done | bar: October 1 to December 1
| Sign Up Enhanced UI | Vasquez, Kyle T. | 2024-11-02 | 2024-11-09 | To-Do | bar: October 1 to December 1
BROWSE PETS
| Browse Pets Functionalities | Evangelista, Kaye Aizerner | 2024-10-13 | 2024-10-14 | Done | bar: October 1 to December 1
| Browse Pets UI with Styles | Evangelista, Kaye Aizerner | 2024-10-13 | 2024-10-14 | Done | bar: October 1 to December 1
| Browse Pets Enhanced UI | Evangelista, Kaye Aizerner | 2024-11-02 | 2024-11-09 | Done | bar: October 1 to December 1
ADD PET FORMS
| Add Pet Forms Functionalities | Evangelista, Kaye Aizerner | 2024-10-01 | 2024-10-02 | Done | bar: September 4 to December 1
| Add Pet Forms UI with Styles | Evangelista, Kaye Aizerner | 2024-10-13 | 2024-10-14 | Done | bar: October 1 to December 1
| Add Pet Forms Enhanced UI | Evangelista, Kaye Aizerner | 2024-11-07 | 2024-11-14 | Done | bar: October 1 to December 1
VIEW PET
| View Pet Functionalities | Evangelista, Kaye Aizerner | 2024-10-14 | 2024-10-15 | Done | bar: October 1 to December 1
| View Pet UI with Styles | Evangelista, Kaye Aizerner | 2024-10-14 | 2024-10-15 | Done | bar: October 1 to December 1
| View Pet Enhanced UI (pop-up) | Evangelista, Kaye Aizerner | 2024-11-02 | 2024-11-09 | Done | bar: October 1 to December 1
ADOPTION APPLICATION FORM
| Adoption Application Form Functionalities (user) | Vasquez, Kyle T. | 2024-10-12 | 2024-10-13 | Done | bar: October 1 to December 1
| Adoption Application Form View and Functionality (shelter) | Vasquez, Kyle T. | 2024-10-18 | 2024-10-27 | Done | bar: October 1 to December 1
| Adoption Application Form UI with Styles (shelter) | Vasquez, Kyle T. | 2024-10-18 | 2024-10-27 | Done | bar: October 1 to December 1
| Adoption Application Form UI with Styles (user) | Vasquez, Kyle T. | 2024-10-12 | 2024-10-13 | Done | bar: October 1 to December 1
| Adoption Application Form Enhanced UI (user) | Catubig, Niña Margarette | 2024-11-03 | 2024-11-11 | Done | bar: October 1 to December 1
| Adoption Application Form Enhanced UI (shelter) | Vasquez, Kyle T. | 2024-11-15 | 2024-11-23 | Done | bar: October 1 to December 1
MESSAGE
| Message Functionalities | Evangelista, Kaye Aizerner | 2024-10-13 | 2024-10-14 | Done | bar: October 1 to December 1
| Message UI with Styles | Evangelista, Kaye Aizerner | 2024-10-13 | 2024-10-14 | Done | bar: October 1 to December 1
| Message Enhanced UI | Evangelista, Kaye Aizerner | 2024-11-04 | 2024-11-11 | Done | bar: October 1 to December 1
SHELTER DASHBOARD
| Shelter Dashboard Functionalities | Vasquez, Kyle T. | 2024-10-13 | 2024-10-14 | Done | bar: October 1 to December 1
| Shelter Dashboard UI with Styles | Vasquez, Kyle T. | 2024-10-13 | 2024-10-14 | Done | bar: October 1 to December 1
| Shelter Dashboard Enhanced UI | Vasquez, Kyle T. | 2024-11-04 | 2024-11-11 | Done | bar: October 1 to December 1
PET LISTING
| Pet Listing Functionalities | Vasquez, Kyle T. | 2024-10-15 | 2024-10-16 | Done | bar: October 1 to December 1
| Pet Listing UI with Styles | Vasquez, Kyle T. | 2024-10-15 | 2024-10-16 | Done | bar: October 1 to December 1
| Pet Listing Enhanced UI | Vasquez, Kyle T. | 2024-11-03 | 2024-11-16 | Done | bar: October 1 to December 1
PENDING REQUEST
| Home UI Added (both shelter and user) | Evangelista, Kaye Aizerner | 2024-10-18 | 2024-10-28 | Done | bar: October 1 to December 1
| Pending Request Functionalities | Evangelista, Kaye Aizerner | 2024-10-18 | 2024-10-21 | Done | bar: October 1 to December 1
| Favorite a Pet (Browse) | Evangelista, Kaye Aizerner | 2024-10-18 | 2024-10-30 | Done | bar: October 1 to December 1
| Redesigned View Pet when Browsing(with favorites) | Evangelista, Kaye Aizerner | 2024-10-18 | 2024-10-30 | Done | bar: October 1 to December 1
| Pending Request Enhanced UI (user) | Catubig, Niña Margarette | 2024-11-15 | 2024-11-23 | Done | bar: October 1 to December 1
| Pending Request Enhanced UI (shelter) (pop-up) | Evangelista, Kaye Aizerner | 2024-11-15 | 2024-11-23 | Done | bar: October 1 to December 1
PET ADOPTED
| Redesigned Messages | Evangelista, Kaye Aizerner | 2024-10-18 | 2024-10-31 | Done | bar: October 1 to December 1
| Notify in messages if Pet is Accepted/Declined | Evangelista, Kaye Aizerner | 2024-10-18 | 2024-10-31 | Done | bar: October 1 to December 1
| Pet Adopted Enhanced UI | Evangelista, Kaye Aizerner | 2024-11-15 | 2024-11-23 | Done | bar: October 1 to December 1
USER DASHBOARD
| User Dashboard Functionalities | Catubig, Niña Margarette | 2024-10-16 | 2024-10-17 | Done | bar: October 1 to December 1
| User Dashboard UI with Styles | Catubig, Niña Margarette | 2024-10-15 | 2024-10-17 | Done | bar: October 1 to December 1
| User Dashboard Enhanced UI | Catubig, Niña Margarette | 2024-11-15 | 2024-11-23 | Done | bar: October 1 to December 1
REQUESTS (USER)
| User Requests Functionalities | Catubig, Niña Margarette | 2024-10-16 | 2024-10-17 | Done | bar: October 1 to December 1
| User Requests UI with Styles | Catubig, Niña Margarette | 2024-10-16 | 2024-10-17 | Done | bar: October 1 to December 1
| User Requests Enhanced UI | Catubig, Niña Margarette | 2024-11-15 | 2024-11-23 | Done | bar: October 1 to December 1
FAVORITES (USER)
| User Favorites ( Dashboard ) | Catubig, Niña Margarette | 2024-10-18 | 2024-10-26 | Done | bar: October 1 to December 1
| User Favorites UI with Styles ( Dashboard ) | Catubig, Niña Margarette | 2024-10-18 | 2024-10-26 | Done | bar: October 1 to December 1
| User Favorites Enhanced UI | Catubig, Niña Margarette | 2024-11-15 | 2024-11-23 | Done | bar: October 1 to December 1
ADOPTION HISTORY (USER)
| User Adoption History Functionalities | Catubig, Niña Margarette | 2024-10-18 | 2024-10-26 | Done | bar: October 1 to December 1
| User Adoption History UI with Styles | Catubig, Niña Margarette | 2024-10-18 | 2024-10-26 | Done | bar: October 1 to December 1
| User Adoption History Enhanced UI | Catubig, Niña Margarette | 2024-11-15 | 2024-11-23 | Done | bar: October 1 to December 1
PROFILE
| Profile filling functionalities | Catubig, Niña Margarette | 2024-10-14 | 2024-10-15 | Done | bar: October 1 to December 1
| Profile Editing functionalities | Catubig, Niña Margarette | 2024-10-18 | 2024-10-26 | Done | bar: October 1 to December 1
| UI with Styles (profile filling) | Catubig, Niña Margarette | 2024-10-15 | 2024-10-16 | Done | bar: October 1 to December 1
| UI with Styles (profile editing) | Catubig, Niña Margarette | 2024-10-18 | 2024-10-26 | Done | bar: October 1 to December 1
| Enhanced UI (profile page) | Catubig, Niña Margarette | 2024-11-15 | 2024-11-23 | Done | bar: October 1 to December 1
| Enhanced UI (profile filling) | Catubig, Niña Margarette | 2024-11-15 | 2024-11-23 | Done | bar: October 1 to December 1
| Enhanced UI (profile Editing) | Catubig, Niña Margarette | 2024-11-15 | 2024-11-23 | Done | bar: October 1 to December 1
OTHERS
| Create Navigation Bar | Catubig, Niña Margarette | 2024-10-01 | 2024-10-02 | Done | bar: September 4 to December 1
| Enhanced UI for Navigation Bar | Vasquez, Kyle T. | 2024-10-18 | 2024-10-26 | Done | bar: October 1 to December 1
| Logout Functionality | Evangelista, Kaye Aizerner | 2024-10-01 | 2024-10-02 | Done | bar: September 4 to December 1
| Create main page | Vasquez, Kyle T. | 2024-10-01 | 2024-10-02 | Done | bar: September 4 to December 1
| Landing Page UI with Styles | Vasquez, Kyle T. | 2024-10-03 | 2024-10-17 | Done | bar: October 1 to December 1
| Enhanced UI for main page | Vasquez, Kyle T. | 2024-10-18 | 2024-10-26 | Done | bar: October 1 to December 1
ADOPTION FORM VIEW
| Shelter view adoption request | Evangelista, Kaye Aizerner | 11/29/24 | 11/30/24 | Done | bar: October 1 to December 1
| Shelter view adoption request filter | Evangelista, Kaye Aizerner | 11/30/25 | 2025-01-12 | Done | bar: October 1 to December 1